## Stakeholder Analysis
Oregon Tech Nolij Implementation STAKEHOLDER ANALYSIS
Stakeholder Group | Current Level of Understanding / Attitude | Compelling Aspects / Benefits | Concerns/ Challenges | Ways to Improve Commitment & Involvement | Notes
STUDENT
General Student Population | none/indifferent | students will see improvements in support from the administrative offices and in the ease of submitting information to the university
EMPLOYEE
Upper Management | good/very supportive | better records accessibility; reduced paper handling costs; improved communication within and between departments; improved long term records security
Business Unit Management | moderate/supportive | same as upper mgmt, plus more timely completion of work | costs of implementation (hardware, disruption of current work and user training); concerns about reliability of records retrievability | meet with unit managers to address their concerns, demo the system, provide contact to current users, have them assist in planning the transation away from paper
Central Administrative Users | little/supportive | same as mgmt | fear of "something new", fear that it will be difficult to use, fear that records will get lost or fail to get processed, fear of job loss | involve users in implementation planning, meet with users to address concerns, provide training
Central IT | good/supportive |  | this is another system to support (where as paper record systems had little impact on IT) | involve group in planning what "supporting the new system" will require; provide access to Nolij Technical Support early
Faculty/Advisors | little/supportive | Advising records (notes, transcripts, etc.) will become available on line, which will make a better historical records trail available at the time of meeting with the student | fear that others may see something they do not intend to share, fear that a lot of their time will be required to scan information | when the records are becoming available to the faculty and advisors on line, demo the system, show them what is required to file records digitally, and address any questions they may have
Student Employees | none/ indifferent |  |  |  | the switch from paper to digital record systems will change what student employees do, but generally, as part time temporary employees, they come into the situation and accept it as it is.

## Communication Analysis
Oregon Tech Nolij Implementation COMMUNICATION ANALYSIS
Stakeholder Group | Stage of Communication | Purpose of Communication | Take Away | Medium / Method | Resources | Owner | When (Estimated)
ALL USERS
General Demos | Awareness & Understanding | Introduce the concept and benefits of document imaging | ease of system use, accessibilty of data, security of information | Demonstrations which include time for questions and answers. Schedule several which target specific groups | Business Analyst (HWP) | Sponsor | early in project, several 1 hour demo's
Admissions Registrar & Distance Ed teams
Focused Demo | Understanding & Commitment | To display how the system can assist them in their work, introduce the scope of customization which can taylor the system to their needs | That the system can be configured to work for them, that it is easy and secure. | Demonstration which is focused on the specific area of work of the attendees, in small environment which is conducive to discussion and question answering. Include all (user) team members and members from the technical staff who will be working with their implementation | Business Analyst (HWP) & IT staff | IT Mgmt and Team Mgmt | Early in design phase
Planning Sessions | Understanding & Commitment | To seek input on their view of system requirements. Initiate planning | That the system is being designed to meet their needs, that it is easy to use, and will speed up their work. | Group "round table" meeting environment, with ability to project Nolij and Banner. | Business Analyst (HWP) & IT staff | Dept Mgmt | Regularly throughout design. Often takes 4-5 one an a half hour sessions
Submission of Project Specification & Acceptance | Commitment | To solidify understanding of agreements and plans; including ancillary changes the group will be required to implement. | Understanding that the plan is in place, and a commitment to the schedule. | Document submitted to Dept. Mgmt (and usually shared with all team members who have participated) | Business Analyst (HWP) & IT staff | Dept Mgmt | End of Planning Phase
Regular Development Progress Reports; (recipient groups include Sponsor, Dept Mgmt, IT Mgmt) | Commitment | To keep the teams appraised of progress, committed to the agreed upon timeline, or made aware of any anticipated changes to the timeline. | That things are on schedule (so that they can plan their staff resources), or an alert that changes may need to be made. | Email. | Business Analyst (HWP) & Developer | Sponsor, Dept Mgmt, | Development Phase
Training Sessions | Action | to train the users and test the product | Knowledge of how the product will work in the users' environments; and reassurance that it will work for them. | Computer Lab. | Business Analyst (HWP), IT contact for group, Team Mgmt. | Dept Mgmt, IT Mgmt | End of Development Phase
Associated Groups | Action | To provide other departments with information about how the new implementation will impact interactions between the departments | Understanding any inter-department interaction changes which will be necessary because of the new software. | Document detailing any change in inter-departmental processes and the timeline for implementing them. Developing this plan and document may best be done in conjunction with the other department(s), well before implementation time. | Dept Mgmt (from both the primary depts and the associated depts) | Dept Mgmg | Toward the end of the Planning Phase
Business Services Team
Student Affairs Team
Human Resources Team
<Project Name> COMMUNICATION ANALYSIS (Alternate)
Timeline | Stakeholder Group | Purpose of Communication | Take Away | Medium / Method | Owner

## Training Analysis
Oregon Tech Nolij Implementation TRAINING ANALYSIS
Stakeholder Group | Training Needs | Opportunities | Medium / Methods | Resources | When
Admissions Team
Management | Understand the Workflow and how to reassign tasks if workers are absent | Group Training at "Go Live" | 1. Review Workflow Diagram. 2 . Practice with the system using actual students. First walk through several shared examples, then work individually on several examples. 3. Answer questions in the group setting. 4. Be available in Dept. to answer individual's questions for first half day of actual use | Business Analyst (HWP), Workflow Diagram, Example Data, Computer Lab with access to Software and Data | Half Day at Go Live
Regular Users | Understand the Workflow and how to execute their own tasks within it | Group Training at "Go Live" | 1. Review Workflow Diagram. 2 . Practice with the system using actual students. First walk through several shared examples, then work individually on several examples. 3. Answer questions in the group setting. 4. Be available in Dept. to answer individual's questions for first half day of actual use | Business Analyst (HWP), Workflow Diagram, Example Data, Computer Lab with access to Software and Data
Departmental Admin | Understand the administrative functions of Nolij | Individual training just after "Go Live training" | Meeting to review the method of user setup, and the meaning of each permission setting | Business Analyst (HWP)
Registrar's Team
Management | Understand the Workflow and how to reassign tasks if workers are absent | Group Training at "Go Live" | 1. Review Workflow Diagram. 2 . Practice with the system using actual students. First walk through several shared examples, then work individually on several examples. 3. Answer questions in the group setting. 4. Be available in Dept. to answer individual's questions for first half day of actual use | Business Analyst (HWP), Workflow Diagram, Example Data, Computer Lab with access to Software and Data
Regular Users | Understand the Workflow and how to execute their own tasks within it | Group Training at "Go Live" | 1. Review Workflow Diagram. 2 . Practice with the system using actual students. First walk through several shared examples, then work individually on several examples. 3. Answer questions in the group setting. 4. Be available in Dept. to answer individual's questions for first half day of actual use | Business Analyst (HWP), Workflow Diagram, Example Data, Computer Lab with access to Software and Data
Departmental Admin | Understand the administrative functions of Nolij | Individual training just after "Go Live training" | Meeting to review the method of user setup, and the meaning of each permission setting | Business Analyst (HWP)
Distance Ed Team
Management | Understand the Workflow and how to reassign tasks if workers are absent | Group Training at "Go Live" | 1. Review Workflow Diagram. 2 . Practice with the system using actual students. First walk through several shared examples, then work individually on several examples. 3. Answer questions in the group setting. 4. Be available in Dept. to answer individual's questions for first half day of actual use | Business Analyst (HWP), Workflow Diagram, Example Data, Computer Lab with access to Software and Data
Regular Users | Understand the Workflow and how to execute their own tasks within it | Group Training at "Go Live" | 1. Review Workflow Diagram. 2 . Practice with the system using actual students. First walk through several shared examples, then work individually on several examples. 3. Answer questions in the group setting. 4. Be available in Dept. to answer individual's questions for first half day of actual use | Business Analyst (HWP), Workflow Diagram, Example Data, Computer Lab with access to Software and Data
Departmental Admin | Understand the administrative functions of Nolij | Individual training just after "Go Live training" | Meeting to review the method of user setup, and the meaning of each permission setting | Business Analyst (HWP)
IT Team / Support Personnel
Developers | Understand Roles and Permission Setup | Individual training session final steps of the Workflow Creation | Work with developer at their own work site | Business Analyst (HWP)
First Line Support | Understand how the system looks to the user, and typical "user" issues | Participate in Group "Go Live Training", then separate session to discuss "Typical Issues" | Meeting to discuss typical user support issues. | Business Analyst (HWP), Computer Lab with access to Software and Data (or Desk if only one individual)

## Support Analysis
Oregon Tech Nolij Implementation SUPPORT ANALYSIS
Stakeholder Group | Potential Issues | Resources | Owners / Subject Matter Expert | Notes
Departmental Users
| Access Issues | Nolij Departmental Admin | OT's Normal Access Request Team
| Java Issues | IT Support; Nolij Departmental Admin | IT DBA/Sys Admin in conjunction with the Developers
| Workflow not functioning as expected | Dept. Mgmt; Business Analyst; Developer | Business Analyst & Developer
| "Lost" Documents | Nolij Departmental Admin; IT DBA/SYS Admin | Developers & IT DBA/SYS Admin team
| Scanner issues/questions | Nolij Departmental Admin; IT Support | IT Support
Department Management
| Changing Business Requirements precipitate need for workflow change | Business Analyst and Developer | Dept Mgmt/ Business Analyst and Developer
| New or Terminated Employees | Nolij Departmental Admin; OT's Normal Access Request Team | Dept Mgmt/ Nolij Departmental Admin & OT's Normal Access Request Team
| Upgrade testing/timing issues | Business Analyst and Dept. Mgmt | Dept Mgmt / Business Analyst

## Support Design
Oregon Tech Nolij Implementation LEVELS OF SUPPORT
Symptom | Initial Support Contact | Organization/Owner | Resources | Will Field Questions from… |  |  | Escalation Paths
|  |  |  | Users | Mgmt | Dept Tech | 1st Level | 2nd Level
Can't access software - Java issues | Dept Technical Contact | Dept Mgmt | Support Notes | y | y |  | Network Help Desk | Nolij Support in Development
Can't access software - Permission issues | Dept Technical Contact | Dept Mgmt | Standard Permission/Access procedures | y | y |  | OT Access Team
Workflow not functioning as expected | Dept Mgmt | Dept Mgmt | Workflow design documentation | y |  | y | Nolij Support in Development
"Lost" Documents | Dept Technical Contact | Dept Mgmt/ Nolij Sys Admin/DBA |  | y | y |  | Nolij Support in Development | Nolij Sys Admin/DBA
Scanner issues/questions | Dept Technical Contact | Dept Mgmt | Documentation which was received with scanner | y | y |  | Nolij Support in Development | Scanner Vendor Help Desk
Changing Business Requirements precipitate need for workflow change | Business Analyst/ Nolij Support in Development | Dept Mgmt | Workflow design documentation, new business requirements |  | y |  | After new plan is developed, then Nolij Development
New or Terminated Employees | OT Access Team | Dept Mgmt | Regular Access Procedures |  | y | y
Upgrade testing/timing and implementation planning | Business Analyst/ Nolij Support in Development | Dept Mgmt | Implementation Plan, Perceptive Release Notes | y | y | y | Nolij Support in Development, Nolij Sys Admin/DBA | Perceptive Software
Note on A4: T. Aitcheson: The general philosophy indicated here is that some users will be identified to play a de facto or informal role in providing assistance to other users of the portal, while others will others will fill this role as part of their official duties. Finally, some will play a "front-line" role of sorts in fielding portal questions and support requests.
Note on B4: T. Aitcheson: Add names of individual as identified