## RACI
RACI Chart
| R - Responsible | Those who do the work to achieve the task.
| A - Accountable | The one ultimately answerable for the correct and thorough completion of the deliverable or task, and the one from whom those designated as Responsible are delegated work. There must be one, and only one Accountable party specified for each task or deliverable.
| C - Consulted | Those whose opinions are sought, typically subject matter experts; and with whom there is two-way communication
| I - Informed | Those who are kept up-to-date on progress and with whom only one-way communication is required
Activity | ECS Programmers | ECS Systems | Helpdesk | Page Owner | App Owner | CWS | ACUG | Other | Notes
Existing Content
Change titles, text, link name or destination | R |  |  | C,A
Spelling correction on page | R |  |  | I,A
Correct invalid link | R |  |  | C,A |  |  |  |  | Confirm correction with page owner after updating
Modify look and feel of existing content | R |  |  | C,A
New Content
Identify where to add new content
- When customer owns the page |  |  |  | A,R
- Where no obvious fit |  |  | I | C |  |  | R,A | R | Connie will bring to ACUG
Portlets
Develop new portlet | C |  |  |  | A,R | C
Test new portlet | R |  | I | C | A,R | C
Install new portlet on portal | R,A | I | I | C | C | I
Pages
Decide to create new page | [6 empty] | A,R | R | Connie
Design new page | R |  |  | A,R |  |  |  | I,C | Communications to be informed/consulted
Install new page on portal | R |  | I | C,A
Development
Decide to develop new solution
- When customer owns the page |  |  |  | A,R
- Where no obvious fit |  |  | I | A |  |  | C | R | Connie will bring to ACUG
Identify who will develop new solution | I |  |  |  |  | I |  | A,R | Whichever group owns page or ACUG
Portal Decisions
Decide content changes affecting multiple pages |  |  |  | A,R |  |  |  |  | Page owners to meet and decide
Determine portal look and feel (color, fonts, effects, graphics) | I |  |  | I |  | C |  | R, A | Communications is the "other"
Modify style guide | I |  |  | I | I | R |  | R,A | CWS responsible for CSS components, Communication for language
Decide who views which pages | I |  | I | A,R
Administrative access decisions (admin, announcements) | I | [5 empty] | R,A
Determine how to use new features | C |  | C | C |  |  | R,A |  | Communities, allowing customization
Annoucements
Create, modify or remove an annoucement | [7 empty] | A,R | Announcers do this
Modify list of allowed announcers | R | [6 empty] | C,A | Catherine to validate requests
Functional adjustments
Deploy look and feel changes | R |  | I | I |  | R,A |  | C | Communications needs to be involved
Enable authentication of application through OSU's CAS |  | R | I |  | R,A
Modify CAS process (timeouts, upgrades, outages, logic changes) |  | R,A | I |  | I
Add or modify role or dynamic group definitions | R |  | I | C |  |  | C,A |  | If this is just for a page, the page owner will be accountable
Add or change tabs | R |  | I |  |  |  | C,A
Add or change button functionality | I |  | I | A,R |  | R |  |  | Welcome page
Add or modify My Personal Pages functions | R |  | I | I |  |  | C,A
Modify portal code or major features (upgrades, turning on/off functionality, maintenance) | R,A | R | I | C | I | C | C | I | Communications needs to hear of change as well