## Sheet1
Description | Objective | Format | Audience | Draft by | Sent from | Release on/Frequency | Notes
Project update sponsors | Current status on milestones, upcoming tasks and open issues | email | IT governance team | PM | PM | Bi-weekly
Project update | Current events, with links to FAQ's | blog post | OSU community | core team | core team | Bi-weekly + key milestones
Updates for committees | Provide update and solicit feedback from OSU committees | meeting | OSU community via established committees | core team to schedule and attend | n/a | varies - ongoing December - June
Stage 1 evaluation Barometer press release | provide overview of project scope and timeline | email w/ Word doc | Students and all who read the Barometer | Lynn | Lynn | sent on 1/27/2014
Invitation to Extended evaluation team | Describe scope of extended team responsibilities & request participatoin | email | Extended team members | PM | project sponsor | 2013-12-03
RFP and contact with vendors | Inform OSU on RFP and give instructions on contact with vendors | email; web site | Instructors, Chairs, Deans (and others?) | core team | project sponsor | 2013-12-05
Extended team stage 1 evaluation instructions | Provide instructions on how to evaluate RFP responses, key deadlines, etc. | email | extended team and specialists | core team |  | 2014-01-10
Core + Extended team stage 1 ranking | Rank responses and record results | meeting | core and extended teams; specialists |  |  |  | sent to proj. sponsors 2/12/2014
Stage 1 evaluation sponsor update | Share evaluation results w/ IT gov team. Validate short list. | meeting + email | IT governance team | core team | n/a | 2014-01-30
Stage 1 outcome update | Announce short list and describe next steps | web site; blog post; emails to deans/chairs? | OSU community | core team | project sponsor | 2014-02-07
Stage 2 kickoff event | Announce details of Stage 2 evaluation; opportunities for participation; ways to ask q's and provide feedback | Event + communication | OSU community |  |  | week of April 7 (?) or mid-Winter term? | Need to get a presence at Cascades; email to Natalie Dollar and Julie Gess-Newsome on 3/27. Newport? Whom to ask?
Extended team stage 2 evaluation instructions | Provide instructions on how to evaluate RFP responses, key deadlines, etc. | email | extended team and specialists | core team | project sponsor
Core + Extended team stage 2 ranking | Rank responses and record results | meeting | core and extended teams; specialists
Stage 2 evaluation sponsor update | Share evaluation results w/ IT gov team. | meeting + email | IT governance team | core team | n/a
Final summary report and recommendation from core evaluation team |  | report |  |  |  | 2014-06-25
Oregon Stater article | Connect with broader OSU community | article | OSU alums and supporters |  |  | in S2014?
OSU Marketing and Communication | Connect with broader OSU community | news release? | OSU stakeholders and supporters |  |  | S2014?